Development Roadmap and Implementation Strategy

Project: PocketLedger — Personal Expense Tracker

Prepared by: Varsha

Role: Junior Software Developer Intern

Version 1.0 — Week 3 Deliverable

# 1. Introduction

This document builds on the Week 1 Software Requirements Document and the Week 2 System Architecture Design to define a concrete development roadmap and implementation strategy for PocketLedger. It breaks the project into logical development stages, schedules milestones against a realistic 10-week timeline, selects and justifies a development methodology, estimates effort per stage, identifies risks with mitigation plans, and describes how modules will be integrated and tested. The plan assumes a single junior developer working roughly 15-20 hours per week, consistent with a part-time internship schedule.

# 2. Stage Planning

The project is divided into five sequential stages, with the coding stage further broken into four sprints aligned to the four modules defined in the Week 2 architecture document (Auth, Expense, Budget & Report, and Integration). Coding is sequenced so that the Auth Module is built first, since every other module depends on it for request authentication.

Figure 1: 10-week development roadmap

- Stage 1 — Planning & Requirements (Week 1): Already complete; carried forward from the Week 1 SRD.

- Stage 2 — Design (Weeks 2–2.5): Architecture and module breakdown, carried forward from the Week 2 document; database schema finalized during this stage.

- Stage 3 — Coding, in four sprints (Weeks 2.5–8): Auth Module, then Expense Module, then Budget & Report Module, then Integration Module, each built and unit-tested before the next begins.

- Stage 4 — Testing & QA (Weeks 8–9.5): Integration testing across all modules, cross-browser checks, and bug fixing.

- Stage 5 — Deployment (Weeks 9.5–10): Production deployment and final smoke testing.

# 3. Milestone Definition

| Milestone | Deliverable | Deadline |
| --- | --- | --- |
| M1: Requirements sign-off | Week 1 SRD (complete) | End of Week 1 |
| M2: Architecture sign-off | Week 2 architecture document (complete) | End of Week 2.5 |
| M3: Auth Module complete | Working registration/login with JWT issuance; 90%+ unit test coverage on auth logic | End of Week 4 |
| M4: Expense Module complete | Full CRUD for expenses; category validation working | End of Week 5.5 |
| M5: Budget & Report Module complete | Budget-status calculation and dashboard summary working end-to-end | End of Week 7 |
| M6: Integration Module complete | CSV export functional; email-alert and bank-import interfaces stubbed for future use | End of Week 8 |
| M7: QA sign-off | All P1 (blocking) bugs resolved; cross-browser checklist passed | End of Week 9.5 |
| M8: Production deployment | Live, publicly accessible application | End of Week 10 |

# 4. Implementation Strategy

## 4.1 Methodology: Agile (Scrum-inspired, solo adaptation)

This project adopts an Agile approach rather than Waterfall, primarily because the SRD (Week 1) already flagged scope creep as the highest-impact risk, and Agile's short feedback loops make scope drift visible within a week rather than at the end of the project. A pure Waterfall approach — where all coding happens only after design is 100% finalized — was rejected because it would delay discovering integration problems (e.g., a category-validation edge case between the Expense and Budget modules) until Week 8, with little time left to fix them.

Since this is a single-developer project, standard Scrum ceremonies are adapted rather than used literally: there is no daily standup (no team to synchronize with), but each sprint still opens with a 30-minute sprint planning session and closes with a self-review against the sprint's Definition of Done, mirroring the accountability a stand-up would otherwise provide.

## 4.2 Sprint Breakdown

| Sprint | Duration | Goal | Definition of Done |
| --- | --- | --- | --- |
| Sprint 1 | 1.5 weeks (Weeks 2.5–4) | Auth Module | User can register, log in, and receive a JWT; invalid credentials are rejected; passwords are hashed, never stored in plaintext |
| Sprint 2 | 1.5 weeks (Weeks 4–5.5) | Expense Module | User can create, edit, delete, and list expenses; invalid amounts/dates are rejected with clear error messages |
| Sprint 3 | 1.5 weeks (Weeks 5.5–7) | Budget & Report Module | User can set a budget; dashboard shows correct running total and budget-status flag (matching Week 2, Section 4) |
| Sprint 4 | 1 week (Weeks 7–8) | Integration Module | CSV export produces a valid, correctly formatted file for a selected date range |

# 5. Resource Estimation

Effort is estimated in developer-hours, assuming roughly 15-20 hours of available time per week. Total estimated effort is 155 hours across 10 weeks, which is within the availability window and leaves a buffer of approximately 15-20% for the challenges listed below.

| Stage | Estimated Hours | Key Challenges | Mitigation |
| --- | --- | --- | --- |
| Design | 12 hrs | Under-specifying the database schema, leading to rework later | Reuse the schema implied by the Week 2 module breakdown (Section 3.4) rather than redesigning from scratch |
| Sprint 1: Auth | 20 hrs | Getting JWT expiry and refresh logic wrong, causing users to be logged out unexpectedly | Use a well-documented library default (e.g., a fixed 24-hour token expiry) instead of building custom refresh-token logic for the MVP |
| Sprint 2: Expense | 22 hrs | Validation edge cases (e.g., negative amounts, future-dated expenses) discovered late | Write validation unit tests before writing the UI form, so edge cases are defined upfront |
| Sprint 3: Budget & Report | 25 hrs | Aggregation queries becoming slow as test data grows | Add a database index on (user_id, date) early, rather than after a performance problem appears |
| Sprint 4: Integration | 16 hrs | CSV formatting edge cases (commas inside notes, special characters) | Use a maintained CSV-writing library rather than manually joining strings with commas |
| Testing & QA | 30 hrs | Limited time to test on multiple real devices | Prioritize the two most common browser/screen-size combinations first (Chrome desktop, and a 375px-wide mobile view), per NFR-5 in the Week 1 SRD |
| Deployment | 10 hrs | First-time deployment configuration errors (environment variables, database connection strings) | Deploy a minimal "hello world" version of the API in Week 2 to validate the hosting pipeline early, rather than deploying for the first time in Week 10 |
| Buffer / contingency | 20 hrs | Unplanned rework across any stage | Reserved explicitly rather than silently absorbed into other estimates, so schedule slippage is visible rather than hidden |

# 6. Risk Assessment

| Risk | Dependency | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Sprint 1 (Auth) overruns, delaying all downstream sprints | Sprints 2-4 all depend on a working Auth Module | Medium | Time-box Sprint 1 to 1.5 weeks; if incomplete, ship with a simplified session mechanism and revisit token refresh post-MVP |
| Free-tier hosting limits cause deployment failures in Week 10 | Deployment stage depends on the hosting provider chosen in Week 2 | Medium | Deploy a minimal test version in Week 2 (see Section 5) instead of discovering limits for the first time at final deployment |
| Scope creep re-introduces excluded features (e.g., multi-user support) | None — self-imposed risk | Medium | Re-check every new feature idea against the Week 1 SRD's explicit out-of-scope list (Section 5.2) before implementing it |
| Underestimated testing time due to limited access to multiple devices | Testing & QA stage depends on device/browser access | Low | Use browser developer tools to simulate the 360px mobile viewport (NFR-5) rather than requiring a physical device for every test |

# 7. Integration and Testing Plan

Modules are integrated incrementally rather than all at once at the end, directly reflecting the layered, independently-testable design from the Week 2 architecture document. After each sprint, the newly completed module is integrated with previously completed modules and a short integration test is run before moving to the next sprint — rather than waiting until Week 8 to discover that, for example, the Expense Module and Budget Module disagree about how a deleted category should be handled.

## 7.1 Unit Testing

- Each repository function (e.g., getExpensesByUser) is tested against a test database with known seed data, verifying correct filtering and correct handling of empty results.

- Each business logic function (e.g., budget percentage calculation) is tested with boundary values: exactly 79%, exactly 80%, and exactly 100% of budget, to confirm the threshold logic in FR-8 (Week 1 SRD) behaves correctly at the edges, not just in the middle of the range.

## 7.2 Integration Testing

- After Sprint 2: verify that an expense created through the API is correctly retrievable and correctly excluded when its category is deleted.

- After Sprint 3: verify that adding an expense correctly updates the budget-status flag returned by the dashboard endpoint, using the same worked example introduced in the Week 2 document (an ₹1,200 grocery expense pushing total spend to 84% of a ₹15,000 budget).

- After Sprint 4: verify that a CSV export for a given month contains exactly the same totals as the dashboard for that month, confirming the Integration Module and Budget & Report Module agree on the underlying data.

## 7.3 Manual and Cross-Browser Testing

- Manual click-through testing of the full user journey (register → add three expenses → set a budget → view dashboard → export CSV) is performed once per sprint, not only at the end, to catch UX issues early.

- Cross-browser testing is performed against the two highest-priority targets identified in Section 5 (Chrome desktop and a 375px mobile viewport) before wider browser testing, given the fixed 30-hour testing budget.

# 8. Conclusion

This roadmap sequences PocketLedger's development into five stages and four sprints across a 10-week, 155-hour plan, with an explicit 20-hour contingency buffer. The Agile methodology was chosen specifically because it surfaces integration problems early, which directly addresses the highest-priority risk (scope creep and late-discovered defects) identified in the Week 1 SRD. Combined with the Week 1 requirements and Week 2 architecture, this document is intended to allow implementation to begin immediately, with clear, testable milestones marking progress at each stage.